## Scheduling&Progress
Project Scheduling and Progress Tracking |  |  |  |  | Overall Progress: | 0% | [20 empty] | 0%
Project Timeline : | Planned |  | Actual | time axis 2013-05-27 to 2013-07-26
Activities | Start | Duration(days) | Start | Duration | Manpower Allocation | Progress
Development of site template and background | 2013-05-27 | 7 |  |  | Hasan, Sri | 0% | bar: 2013-05-27
Basic Template Development |  |  |  |  | Hasan | bar: 2013-05-27
Additional Features |  |  |  |  | Sri | bar: 2013-05-27
Integration&Standardization |  |  |  |  | Hasan, Sri | bar: 2013-05-31
DDL Module content & Product Information Input | 2013-05-28 | 24 |  |  | Teo Huei, Hasan | 0% | 2013-05-28: 0
Mortise Product Content & Manuals |  |  |  |  | Hasan |  | 2013-05-28: 0
Deadbolt & Rim Product Content & Manuals |  |  |  |  | Teo Huei |  | 2013-06-04: 0
Gallery,Wiring Diagrams Module |  |  |  |  | Hasan & Teo Huei |  | 2013-06-17: 0
VCP (Intercom) Module content & Product Info Input | 2013-05-28 | 24 |  |  | Marconi | 1.333% | 2013-05-28: 1.3333
Product Content |  |  |  |  | Marconi | 2% | 2013-05-28: 2
Product Manuals |  |  |  |  | Marconi | 2% | 2013-06-06: 2
Diagrams and Gallery Modules |  |  |  |  | Marconi |  | 2013-06-16: 0
Time Man. & Access Control module content input | 2013-05-28 | 24 |  |  | Varshini, Sri | 0% | 2013-05-28: 0
Product Content |  |  |  |  | Varshini |  | 2013-05-28: 0
Product Manuals |  |  |  |  | Sri (Varshini partially) |  | 2013-06-04: 0
Gallery,Wiring Diagrams Module |  |  |  |  | Varshini, Sri |  | 2013-06-16: 0
Resources/Database Configuration | 2013-06-25 | 14 |  |  | Hasan, Sri |  | 2013-06-25: 0
Home Automation Module | 2013-06-25 | 14 |  |  | Teo Huei, Marconi, Varshini |  | 2013-06-25: 0
Consolidation of Modules & Design testing | 2013-07-11 | 10 |  |  | Team |  | 2013-07-11: 0